## Data
Requirements Traceability Matrix
Project Name: |  | Ascend
| Cross Testing Developer | Shehap Elhadary
Project Description: |  | E2E Testing and Development of The project.
Requirements |  |  | Testing |  |  | Defects
Module 1: Authenticaton (Tested on Ascend&Linkedin)
Req. ID | Requirements Description | Requirement Type | Test Case ID | Test Description | TEST | Defective | Defect ID | Defect Description | Req. Status
REQ1.1 | Login with valid/invalid credentials | Functional | TC1.1.1 | Tests login with valid credentials, expects landing on homepage. | Pass | No |  |  | Complete
REQ1.1 | Login with valid/invalid credentials | Functional | TC1.1.2 | Tests login with correct email and wrong password, expects error. | Pass | No |  |  | Complete
REQ1.2 | Login with valid/invalid credentials | Functional | TC1.1.3 | Tests login with google/facebool | Fail | YES |  | button doesn't redirect user to facebook/google for authentication | Complete
REQ1.1 | Login with valid/invalid credentials | Functional | TC1.1.3 | Tests login with wrong email and correct password, expects error. | Pass | No |  |  | Complete
REQ1.1 | Login with valid/invalid credentials | Functional | TC1.1.4 | Tests empty email field during login, expects error message. | Pass | No |  |  | Complete
REQ1.1 | Login with valid/invalid credentials | Functional | TC1.1.5 | Tests empty password field during login, expects error message. | Pass | No |  |  | Complete
REQ1.1 | Login with valid/invalid credentials | Functional | TC1.1.6 | Tests if login is casesenstive, expects normal behavior. | Fail | Yes | ADEF01 | Login fails when entering a correct email with different letter casing | Complete
REQ1.2 | Valid/Invalid user signup | Functional | TC1.2.1 | Tests valid signup, expects successful account creation. | Pass | No |  |  | Complete
REQ1.2 | Valid/Invalid user signup | Functional | TC1.2.2 | Tests signup with invalid email format, expects error. | Pass | No |  |  | Complete
REQ1.2 | Valid/Invalid user signup | Functional | TC1.2.3 | Tests signup with weak password, expects error. | Pass | No |  |  | Complete
REQ1.2 | Valid/Invalid user signup | Functional | TC1.2.4 | Tests signup with existing email, expects duplication error. | Pass | No |  | error message is just passing json data without any styling | Complete
REQ1.2 | Valid/Invalid user signup | Functional | TC1.2.5 | Test sign up with invalid name contaning malicious characters | Fail | Yes | ADEF03 | User creates an account although entering invalid name | Complete
REQ1.2 | Valid/Invalid user signup | Functional | TC1.2.6 | Test sign up with empty password | Pass | No |  |  | Complete
REQ1.2 | Valid/Invalid user signup | Functional | TC1.2.7 | Test sign up with empty email | Pass | No |  |  | Complete
REQ1.3 | Forget Password | Functional | TC1.3.1 | Tests forgot password functionalty | Fail | YES | ADEF02 | Forget password fails as no verfication mail is sent | Complete | you create a mail at ascend/mail as the verfication code will be sent to it
Module 2: User Profile
REQ2.1 | Valid/invalid profile name edit | Functional | TC2.1.1 | Tests editing profile name with valid data, expects update success. | Pass | No |  |  | Complete
REQ2.1 | Valid/invalid profile name edit | Functional | TC2.1.2 | Tests editing name with invalid chars, expects validation error. | Fail | Yes | DEF03 | Enables users to enter senstive/ malicous characters | Complete
REQ2.2 | Valid/invalid headline update | Functional | TC2.2.1 | Tests editing headline with valid input, expects update success. | Pass | No |  |  | Complete
REQ2.2 | Valid/invalid headline update | Functional | TC2.2.2 | Tests headline with special chars, expects validation error. | Fail | Yes | DEF04 | Enables users to enter senstive/ malicous characters | Complete
REQ2.3 | Upload valid/invalid cover photo | Functional | TC2.3.1 | Uploads a valid image as cover, expects success. | Pass | No |  |  | Complete
REQ2.3 | Upload valid/invalid cover photo | Functional | TC2.3.2 | Tests uploading corrupted image, expects error. | Pass | Yes | DEF05 | NO ERROR MESSAGE ONLY TIME EXCEPTION MESSAGE | Complete
REQ2.3 | edit cover photo with valid image | Functional | TC2.3.3 | Tests replacing cover photo, expects success. | Pass | No |  |  | Complete
REQ2.4 | Upload valid/Invaid profile photo | Functional | TC2.4.1 | Tests uploading a valid profile photo, expects it saved. | Pass | No |  |  | Complete
REQ2.4 | Upload valid/Invaid profile photo | Functional | TC2.4.2 | Tests uploading broken profile photo, expects error. | Fail | Yes | DEF06 |  | Complete
REQ2.4 | Replace profile photo with valid image | Functional | TC2.4.3 | Tests updating profile photo, expects successful update. | Pass | No |  |  | Complete
REQ2.5 | Add Work Experience to User Profile | Functional | TC2.5.1 | This test verifies that a user can successfully add work experience to their profile. | Pass |  |  |  | Complete
REQ2.6 | Add Skill to User Profile | Functional | TC2.6.1 | This test verifies that a user can successfully add Skills to their profile. | N/A |  |  |  | Partial Completion
REQ2.7 | Add education to User Profile | Functional | TC2.7.1 | Tests adding Education to user profile |  |  |  |  | Partial Completion
REQ2.8 | Add resume to user profile | Functional | TC2.8.1 | Tests Uploading Resume to user profile | N/A |  |  |  | Partial Completion
Module 3: Connections & Networking
REQ3.1 | Search for users by name, company, or industry | Functional | TC3.1.1 | Search by full name and verify results | Pass | No |  |  | Complete
REQ3.1 | Search for users by name, company, or industry | Functional | TC3.1.2 | Search by company – employees listed | Pass | No |  |  | Complete
REQ3.1 | Search for users by name, company, or industry | Functional | TC3.1.3 | Search by industry – relevant users listed | Pass | No |  |  | Complete
REQ3.1 | Search for users by name, company, or industry | Functional | TC3.1.4 | Empty search query – show error/placeholder | Fail | Yes | DEF01 | NO ERROR MESSAGE | Complete
REQ3.2 | Send connection requests to other users | Functional | TC3.2.1 | Send request to valid user | Pass | No |  |  | Complete
REQ3.2 | Send connection requests to other users | Functional | TC3.2.2 | Cannot send request to blocked user | Pass | No |  |  | Complete
REQ3.2 | Send connection requests to other users | Functional | TC3.2.3 | Accept incoming request – user added | Pass | No |  |  | Complete
REQ3.2 | Send connection requests to other users | Functional | TC3.2.4 | Decline request – request removed | Pass | No |  |  | Complete
REQ3.3 | Remove a connection | Functional | TC3.3.1 | Remove user from connections list | Pass | No |  |  | Complete
REQ3.4 | Follow users (without connecting) | Functional | TC3.4.1 | Follow a public profile | Pass | No |  |  | Complete
REQ3.4 | Follow users (without connecting) | Functional | TC3.4.2 | Unfollow a user | Pass | No |  |  | Complete
REQ3.6 | Block/Unblock users | Functional | TC3.5.1 | Block a user | Pass | No |  |  | Complete
REQ3.6 | Block/Unblock users | Functional | TC3.5.2 | Unblock a user | Pass | No |  |  | Complete
REQ3.7 | Manage blocked users list | Functional | TC3.6.1 | View blocked users list | Pass | No |  |  | Complete
Module 4: News Feed & Posts
REQ4.1 | Display posts from connections and followed users chronologically | Functional | TC4.1.1 | Display posts in feed in chronological order | Pass | No |  |  | Complete
REQ4.2 | Create a text post | Functional | TC4.2.1 | Create a new post with only text | Pass | No |  |  | Complete
REQ4.3 | Add media to posts (images, videos, links, documents) | Functional | TC4.3.1 | Add image to post and publish | Pass | No |  |  | Complete
REQ4.3 | Add media to posts (images, videos, links, documents) | Functional | TC4.3.2 | Add video to post and publish | N/A | No |  |  | Partial Completion
REQ4.3 | Add media to posts (images, videos, links, documents) | Functional | TC4.3.3 | Add external link to post and publish | Fail | YES | DEF02 | Did not detect the link in post | Complete
REQ4.3 | Add media to posts (images, videos, links, documents) | Functional | TC4.3.4 | Add document (PDF, DOC) to post and publish | Pass | No |  |  | Complete
REQ4.4 | Edit/Delete post | Functional | TC4.4.1 | Edit an existing post's content and save changes | Pass | No |  |  | Complete
REQ4.4 | Edit/Delete post | Functional | TC4.4.2 | Delete a post and verify it disappears from feed | Pass | No |  |  | Complete
REQ4.5 | Like, Comment, Share posts | Functional | TC4.5.1 | Like a post and verify like count increases | Pass | No |  |  | Complete
REQ4.5 | Like, Comment, Share posts | Functional | TC4.5.2 | Comment on a post and verify comment appears | Pass | No |  |  | Complete
REQ4.6 | Tag users in posts or comments | Functional | TC4.6.1 | Tag a user in a post (e.g., "@John") | Pass | No |  |  | Complete
REQ4.6 | Tag users in posts or comments | Functional | TC4.6.2 | Tag a user in a comment | Pass | No |  |  | Complete
REQ4.9 | Save posts for later reading | Functional | TC4.9.1 | Save a post and verify it appears in "Saved" list | Pass | No |  |  | Complete
REQ4.9 | Save posts for later reading | Functional | TC4.9.2 | Unsave a post and verify it is removed from saved list | Pass | No |  |  | Complete
Module 5: Messaging & Direct Communication
REQ5.1 | Send private messages to connections | Functional | TC5.1.1 | Send a direct message to a connection | Pass | No |  |  | Complete
REQ5.2 | Send media in messages (images, videos, docs) | Functional | TC5.2.1 | Send image in message | Pass | No |  |  | Complete
REQ5.2 | Send media in messages (images, videos, docs) | Functional | TC5.2.2 | Send Corrupted image expecting error message | Fail | Yes | DEF06 | No error message | Complete
REQ5.2 | Send media in messages (images, videos, docs) | Functional | TC5.2.3 | Send document in message | Pass | No |  |  | Complete
REQ5.3 | Get conversation history | Functional | TC5.3.1 | Scroll to view past messages in a chat | Pass | No |  |  | Complete
REQ5.4 | Get unseen messages count | Functional | TC5.4.1 | View badge/count for unread messages | Pass | No |  |  | Complete
Module 6: Notifications
REQ6.2 | Mark notifications as read | Functional | TC6.2.1 | Mark individual notification as read | Pass | No |  |  | Complete
REQ6.4 | Delete notification | Functional | TC6.4.1 | Delete each notification | Pass | No |  |  | Complete
REQ6.5 | Filter by jobs, posts, and mentions | Functional | TC6.5.1 | Filter notifiations by jobs | Pass | No |  |  | Complete
REQ6.5 | Filter by jobs, posts, and mentions | Functional | TC6.5.2 | Filter notifiations by my posts | Pass | No |  |  | Complete
REQ6.5 | Filter by jobs, posts, and mentions | Functional | TC6.5.3 | Filter notifiations by mentions | Pass | No |  |  | Complete
REQ6.3 | Unseen notifications count is displayed as badge | Functional | TC6.3.1 | Unseen notifications count is displayed as badge | N/A | No |  |  | In Progress
Module 7: Jobs & Hiring
REQ7.1 | Search for jobs by keyword, location, and industry | Functional | TC7.1.1 | Enter job-related keyword (e.g., "React Developer") and search | Pass | No |  |  | Complete
REQ7.1 | Search for jobs by keyword, location, and industry | Functional | TC7.1.2 | Enter a city or region (e.g., "Cairo") and search | Pass | No |  |  | Complete
REQ7.1 | Search for jobs by keyword, location, and industry | Functional | TC7.1.3 | Select or enter industry (e.g., "Information Technology") | Pass | No |  |  | Complete
REQ7.2 | Filter jobs by experience level, company, and salary range | Functional | TC7.2.1 | Apply "Experience Level" filter (e.g., Entry-Level) | Pass | No |  |  | Complete
REQ7.2 | Filter jobs by experience level, company, and salary range | Functional | TC7.2.2 | Apply filter for a specific company name | Pass | No |  |  | Complete
REQ7.2 | Filter jobs by experience level, company, and salary range | Functional | TC7.2.3 | Set salary range (e.g., 10k–20k) | Fail | Yes |  | it works fine on ui but it is not linked with backend | Complete
REQ7.3 | Save jobs to apply later | Functional | TC7.3.1 | Tap "Save" on a job listing | Pass | No |  |  | Complete
REQ7.4 | Apply for a job (happy path) | Functional | TC7.4.1 | Click "Apply", fill form, and submit | Pass | No |  | Apply is not working in ascend | Complete
REQ7.4 | Apply for a job (missing info) | Functional | TC7.4.2 | Submit application form without required fields | Pass | No |  |  | Complete
REQ7.5 | View application status (Pending, Viewed, Rejected, Accepted) | Functional | TC7.5.1 | After applying, go to "My Applications" | Fail | No |  | Apply is not working in ascend | Complete
Module 8: Company Pages (Tested on Ascend)
REQ8.1 | Create a company profile | Functional | TC8.1.1 | User navigates to "Create Company" → fills in name, industry, logo, description, and submits | Fail | Yes |  | Upload image only works for small images <0.5 mb | Complete |  | Cannot test this feature as apply is not working
REQ8.2 | Update company details (logo, description, industry, location) | Functional | TC8.2.1 | uploads a new company logo | Fail | Yes |  | Upload image only works for small images <0.5 mb | Complete
REQ8.2 | Update company details (logo, description, industry, location) | Functional | TC8.2.2 | edits the "Description" section and saves | Pass | No |  |  | Complete | Note company cannot post an announcment
REQ8.2 | Update company details (logo, description, industry, location) | Functional | TC8.2.3 | Change industry (e.g., from “Tech” to “Marketing”) and update location field | Pass | No |  |  | Complete | Note: user cannot search company page& following pages in cross is not working properly
REQ8.3 | Post a job opening | Functional | TC8.3.1 | clicks "Post a Job", fills in title, description, and criteria → submits | Pass | No |  |  | Complete
REQ8.4 | Post updates and announcements | Functional | TC8.4.1 | posts a new update (e.g., "We're hiring!") | Fail | No |  | Feature Not impmented | Not Started
REQ8.5 | Manage company followers | Functional | TC8.5.1 | remove follower from the list and count decreases | Fail | No |  | Feature Not impmented | Not Started
REQ8.6 | Track job applications and analytics | Functional | TC8.6.1 | opens a job posting → views all submitted applications | Pass | No |  |  | Complete
REQ8.6 | Track job applications and analytics | Functional | TC8.6.2 | opens analytics dashboard → checks metrics like job views, profile visits | Fail | No |  | Feature Not impmented | Not Started
Module 9: Privacy & Security (Tested on Ascend)
REQ9.1 | Control who can send connection requests | Functional | TC9.1.2 | User sets connection request permission to “Everyone” | Pass | No |  |  | Complete
REQ9.2 | Report/block posts and users for inappropriate content | Functional | TC9.2.1 | User clicks options on a post → selects “Report” → chooses reason → submits | Fail | No |  | Feature Not impmented | Not Started
REQ9.2 | Report a user for abusive behavior | Functional | TC9.2.2 | User opens profile → clicks "More" → selects "Report" → chooses reason → submits | Fail | No |  | Feature Not impmented | Complete
REQ9.3 | Manage blocked users list | Functional | TC9.3.1 | User navigates to Privacy Settings → selects "Blocked Users" | Pass | No |  |  | Complete
REQ9.3 | Manage blocked users list | Functional | TC9.3.2 | User navigates to "Blocked Users" → selects a user → clicks "Unblock" | Pass | No |  |  | Complete
Module 10: Admin Panel (Tested on Ascend)
REQ10.1 | View platform analytics | Functional | TC10.1.1 | Admin logs into the panel → Navigates to "Analytics" section | Pass | No |  |  | Complete
REQ10.1 | Monitor reports of inappropriate content | Functional | TC10.1.2 | Admin selects a reported post → clicks "Review" → chooses to "Ignore" | Fail | Yes |  | Admin can only delete post, he cannot ignore report | Complete
REQ10.1 | Monitor reports of inappropriate content | Functional | TC10.1.3 | Admin selects a reported post → clicks "Review" → chooses to "delete" | Pass | No |  |  | Complete
REQ10.1 | Monitor reports of inappropriate content | Functional | TC10.1.3 | Admin selects a reported user → clicks "Review" → chooses to "Block user" | Fail | Yes |  | Admin cannot delete/ ban/block user this feature is only in ui | Complete
REQ10.2 | Manage job postings and flagged job listings | Functional | TC10.2.1 | Admin navigates to "Flagged Job Listings" → selects a flagged job -> update status | Pass | No |  |  | Complete
REQ10.2 | Manage job postings and flagged job listings | Functional | TC10.2.2 | Admin opens flagged job → selects "Delete" | Pass | No |  |  | Complete
Module 11: Single payment to Premium Plan (Tested on Ascend)
REQ11.1 | Payment Processing | Functional | TC11.1.1 | User selects Premium Plan → Proceeds to payment → Completes Stripe test mode payment | Pass | No |  |  | Complete
REQ11.3 | Subscription Cancellation | Functional | TC11.3.1 | User navigates to subscription settings → Clicks "Cancel Subscription" → Confirms action | Fail | Yes |  | Cancel feature is not working | Complete
REQ11.3 | Subscription Renewal | Functional | TC11.3.2 | User navigates to subscription settings → Clicks "Renew Subscription" | Fail | No |  | Not implmented | Not Started
REQ11.4 | Prevent Duplicate Subscription | Functional | TC11.4.1 | User with active Premium plan attempts to buy again | Pass | No |  |  | Complete
REQ11.5 | Access Restrictions on Free Plan | Functional | TC11.5.1 | Free plan user attempts to exceed connection/message/application limits | Fail | No |  | Cannot test it as user cannot apply, send request, message anyone | Not Started
REQ11.4 | Validate premium plan | Functional | TC11.6.1 | Validate Premium plan feautres | Fail | No |  | Cannot test it as user cannot apply, send request, message anyone | Not Started

## Status (hidden)
Req. Status | Sum of Req. ID
Not Started

## Sheet1
TEST STATUS | Count | REQ. STATUS | Count
Pass | 75 | Complete | 93
Fail | 25 | In Progress | 1
Total | 100 | Not Started | 7
|  | Partial Completion | 4
|  | Total | 105